## Timeline
|  | StartDate | EndDate | Duration | Task | Dependency | Comments
|  | 2018-03-05 | 2018-03-08 | 4 | 1. pick location and get home address
|  | 2018-03-08 | 2018-03-11 | 4 | 2. randomly assign to treatment (keep the list) | 1. pick location and get home address | before print mailing labels
|  | 2018-03-09 | 2018-03-15 | 7 | 3. collect and clean pretreatment data (once) | 1. pick location and get home address | can be in parallel with mailing material preparation
|  | 2018-03-05 | 2018-03-11 | 7 | 4. prepare material | 1. pick location and get home address | follow the local regulations of solid waste management division
|  | 2018-03-12 | 2018-03-15 | 4 | 5. print material (color), labels and prepare envelops | 2. randomly assign to treatment (keep the list) 4. prepare material
|  | 2018-03-16 | 2018-03-16 | 1 | 6. mail the material | 5. print material (color), labels and prepare envelops | assume it takes about a week to deliver
mail | 2018-03-23 | 2018-03-23 | 2018-04-05 | 14 | 7. collect and clean raw data (twice, once per week) | 6. mail the material
all data done | 2018-04-12 | 2018-04-06 | 2018-04-19 | 14 | 8. Analyze data and complete the final paper | 7. collect and clean raw data (twice, once per week)
|  | 2018-04-20 | 2018-04-20 | 1 | 9. Presentation | 8. Analyze data and complete the final paper | assume we do presentation on the last week
Formulas:
EndDate = [StartDate, row below]-1
StartDate = [EndDate, row above]
StartDate = Table1[[#This Row],[EndDate]]-6

## Cost
Treatment Units | 100
assume 400 house | unit price | total cost | notes
color print (one page) | 0.42 | 42 | use OfficeDepot
print labels | $58 / 100 | 116 | use OfficeDepot
envelop & label | $9 /100 | 18 | buy self seal
postage stamp | 0.6 | 60
glue |  | 5 | for mailing label
Total |  | 236
A4 | flyer, post card
12 inches * 7.5 inches, 100 copies, $150, a day, $20 for putting address
Postcard | 100
postcard | 150
postage stamp | 60
mailing label | 20
Total | 230
Item | Description | Amount
Postcard printing | 107 copies | 74.13
Postcard printing | samples | 4.62
Postage Stamp | 100 units | 53
Total |  | 131.75